## Instructions
Emagine U At Play — UAT Checklist
End-to-end User Acceptance Testing checklist for the daycare + therapy management system
How to use this workbook
1. Open the "UAT Checklist" tab. It lists every test case across all 22 modules, in build order.
2. Work through it top to bottom, or use the filter arrows on row 1 to test one module at a time.
3. For each row: perform the Steps to Execute, compare the real result to Expected Result, then fill in Status, Actual Result / Comments, Tested By, and Date Tested.
4. Only edit the columns Status, Actual Result / Comments, Tested By, and Date Tested — every other column is the test spec itself and shouldn't be changed.
5. Check the "Summary" tab any time for a live pass/fail count per module — it updates automatically from your Status entries.
Status column legend
Not Tested — default state, not yet attempted
Pass — behaved exactly as Expected Result describes
Fail — did not match Expected Result — describe what happened in Actual Result / Comments
Blocked — could not be tested (e.g. a dependency isn't built yet)
N/A — doesn't apply to your current setup
Priority column legend
High — core money, safety, or access-control behavior; test these first
Medium — important day-to-day functionality
Low — nice-to-have / cosmetic behavior
Before you start
Make sure the database has been freshly seeded (php artisan migrate:fresh --seed) so admin@daycare.com exists and role/permission data matches what these test cases assume.
Have at least one seeded parent account with a child, and one seeded staff account, so role-based test cases (marked across every module) have something real to check against.

## Summary
UAT Progress Summary
Updates automatically from the Status column on the UAT Checklist tab
Module | Total Cases | Not Tested | Pass | Fail | Blocked | N/A | Pass Rate
Authentication
User Management
Roles & Permissions
Children Management
Guardian-Child Access
Programs
Enrollments
Waitlist
Attendance
Child Daily Logs
Documents
Activities
Drop-in Bookings
Billing - Daycare
Therapy Wing Setup
Therapy Sessions
Therapy Packages
Therapy Billing
Reports
Announcements
Child Safety QR
Security & Non-Functional
TOTAL

## UAT Checklist
# | Module | Test ID | Test Scenario | Steps to Execute | Expected Result | Priority | Status | Actual Result / Comments | Tested By | Date Tested
1 | Authentication | AUTH-01 | Parent self-registration | 1. Go to /register 2. Select role = Parent 3. Fill first/last name, email, phone, password 4. Submit | New user created with role=parent; matching parents profile row created; user auto-logged in and redirected to dashboard | High | Pass
2 | Authentication | AUTH-02 | Staff self-registration | 1. Go to /register 2. Select role = Staff 3. Fill required fields 4. Submit | staff profile row created with default role=teacher; redirected to dashboard | High | Pass
3 | Authentication | AUTH-03 | Duplicate email registration | 1. Register using an email already in the users table | Validation error shown: email already taken; no duplicate row created | Medium | Pass
4 | Authentication | AUTH-04 | Successful login | 1. Go to /login 2. Enter correct email/password 3. Submit | Redirected to dashboard; last_login timestamp updated; session established | High | Pass
5 | Authentication | AUTH-05 | Login with wrong password | 1. Enter correct email, incorrect password 2. Submit | Error "credentials do not match" shown; rate limiter attempt count increases | High | Pass
6 | Authentication | AUTH-06 | Login lockout after repeated failures | 1. Attempt login with wrong password 5 times within a minute 2. Try a 6th time | Locked out with a "too many attempts, try again in X seconds" message | High | Pass
7 | Authentication | AUTH-07 | Deactivated account login | 1. Admin sets a user's is_active = false 2. That user attempts to log in with correct credentials | Login is immediately reversed; "account deactivated" message shown; user is logged out | High | Pass
8 | Authentication | AUTH-08 | Logout | 1. While logged in, click Logout | Session invalidated and token regenerated; redirected to /login | Medium | Pass
9 | Authentication | AUTH-09 | Forgot password request | 1. Go to /forgot-password 2. Submit a registered email | Reset link emailed; success status message shown | Medium | Not Tested
10 | Authentication | AUTH-10 | Reset password via emailed link | 1. Open the emailed reset link 2. Enter and confirm a new password 3. Submit | Password updated; can log in with new password; old password no longer works | Medium | Not Tested
11 | User Management | USER-01 | Admin creates a parent account | 1. Login as admin 2. Go to Create User 3. Select role=Parent, fill fields, submit | User + parents profile row created together in one transaction; Spatie parent role assigned | High | Pass
12 | User Management | USER-02 | Admin creates a staff account | 1. Same as USER-01 with role=Staff | User + staff profile row created; Spatie staff role assigned | High | Pass
13 | User Management | USER-03 | Admin creates another admin account | 1. Same as USER-01 with role=Admin | User row created with admin role; no profile table row required | Medium | Pass
14 | User Management | USER-04 | Non-admin blocked from user creation | 1. Login as staff or parent 2. Attempt to visit /users/create directly | Access denied (403) or redirected away | High | Pass
15 | Roles & Permissions | PERM-01 | Admin sees full sidebar | 1. Login as admin | Every module (Programs, Children, Billing, Staff, Reports, Settings, etc.) appears in the sidebar | Medium | Pass
16 | Roles & Permissions | PERM-02 | Staff sees operational-only sidebar | 1. Login as staff | Staff mgmt, Reports, Settings hidden; operational items (Attendance, Daily Logs, Activities) visible | High | Pass
17 | Roles & Permissions | PERM-03 | Parent sees read-only sidebar | 1. Login as parent | Only view-permitted items appear (own children, invoices, announcements); no create/manage items shown | High | Pass
18 | Roles & Permissions | PERM-04 | Menu item on an unbuilt route doesn't crash | 1. As admin, click a sidebar item still using a raw url (not yet a named route) | Page loads (404 if controller isn't built); shared layout never throws a RouteNotFoundException | Medium | Pass
19 | Roles & Permissions | PERM-05 | Revoking a permission updates the menu | 1. Remove a permission from the staff role 2. Log out and back in as a staff user | The corresponding sidebar item is no longer visible | Low | Pass
20 | Children Management | CHILD-01 | Create a child links a guardian automatically | 1. Admin/staff creates a new child under a parent | A guardian_child row is auto-created linking the billing parent, accepted_at set, access_level=full | High | Pass | User View Needed
21 | Children Management | CHILD-02 | Parent sees only their own children | 1. Login as a parent with 1+ children 2. Go to Children index | Only that parent's linked children appear; no other family's children | High | Pass
22 | Children Management | CHILD-03 | Parent blocked from another family's child | 1. As a parent, note another family's child ID 2. Visit /children/{id} directly | 403 Forbidden — ChildPolicy blocks it | High | Pass | Child View Needed
23 | Children Management | CHILD-04 | Staff sees all active children | 1. Login as staff 2. Go to Children index | All is_active=true children appear regardless of family | Medium | Pass
24 | Children Management | CHILD-05 | Edit a child record | 1. Admin/staff opens a child 2. Updates a field (e.g. allergies) 3. Saves | Update persists and displays correctly on reload | Medium | Pass
25 | Children Management | CHILD-06 | View-only guardian blocked from editing | 1. A guardian with access_level=view_only attempts to edit the child | Edit action is blocked by policy | High | Pass
26 | Children Management | CHILD-07 | Deactivate a child (soft delete) | 1. Admin deactivates a child | is_active becomes false; attendance/billing history remains intact, not deleted | High | Pass
27 | Children Management | CHILD-08 | Emergency contact fields save correctly | 1. Fill ec_name, ec_relationship, ec_phone, ec_authorized_pickup 2. Save and reopen | All four fields display exactly as entered | Medium | Pass
28 | Guardian-Child Access | GUARD-01 | Pending guardian invite has no access yet | 1. Add a second guardian to a child with accepted_at left null | That guardian cannot see the child in their account yet | High | Not Tested
29 | Guardian-Child Access | GUARD-02 | Accepted guardian gains access | 1. Set accepted_at on that guardian_child row (simulating acceptance) | The guardian can now view the child | High | Not Tested
30 | Guardian-Child Access | GUARD-03 | can_pickup flag reflected correctly | 1. Set can_pickup=false for a guardian 2. Check wherever pickup authorization is displayed | Correctly shown as not authorized for pickup | Medium | Not Tested | authorized for pickup - not showing
31 | Guardian-Child Access | GUARD-04 | Primary guardian flag is accurate | 1. Check is_primary on the auto-created guardian_child row from CHILD-01 | The billing parent is marked is_primary=true | Low | Not Tested | is_primary=true not marked in parent list
32 | Programs | PROG-01 | Create a new program | 1. Admin creates a program with name, age range, capacity, billing model | Program saved and appears in the catalog | Medium | Pass
33 | Programs | PROG-02 | State-funded program shows $0 fee | 1. Create/view a program with billing_model=state_funded | monthly_fee displays as $0 / not applicable | Medium | N/A
34 | Programs | PROG-03 | Deactivated program hidden from enrollment | 1. Set a program's is_active=false 2. Start a new enrollment | That program no longer appears as a selectable option | Medium | Pass
35 | Programs | PROG-04 | Drop-in program uses daily_rate | 1. Create a program with service_type=drop_in | daily_rate field is used/required; monthly_fee stays empty | Medium | Fail
36 | Programs | PROG-05 | Non-admin blocked from managing programs | 1. Login as staff or parent 2. Attempt to create/edit a program | Access denied | High | Pass
37 | Enrollments | ENR-01 | Enroll within age range succeeds | 1. Enroll a child whose age fits the program's min/max_age_months | Enrollment created with status=pending or active | High | Pass
38 | Enrollments | ENR-02 | Enroll outside age range blocked | 1. Attempt to enroll a child outside the program's age range | Validation/business rule blocks it with a clear message | High | Pass | It checks enrollment start date, not the child age on today - I think it is ok.
39 | Enrollments | ENR-03 | Enrollment at full capacity goes to waitlist | 1. Enroll into a program already at its capacity limit | Child is routed to the waitlist instead of being enrolled | High | Pass | It is not allowing to enroll which is right.
40 | Enrollments | ENR-04 | Status progression | 1. Move an enrollment from pending → approved → active | Each transition saves correctly; approved_at/approved_by populate on approval | Medium | Pass | Only Pending and Active status are there.
41 | Enrollments | ENR-05 | Withdraw an active enrollment | 1. Withdraw a currently active enrollment | status becomes withdrawn; end_date is recorded | Medium | Pass
42 | Enrollments | ENR-06 | enrolled_by is recorded | 1. Submit a new enrollment as a specific admin/staff user | enrolled_by correctly stores that user's ID | Low | Pass
43 | Waitlist | WAIT-01 | Waitlist position assigned | 1. Add a child to a full program's waitlist | A position number is assigned (e.g. next available) | Medium | N/A | Waitlist module not built in current code: waitlist table has only id/timestamps; no model, screens or routes. Full programs block enrollment (capacity check) instead.
44 | Waitlist | WAIT-02 | Offer a waitlist slot | 1. A spot opens; change status from waiting to offered | Status updates correctly; child is notified per your process | Medium | N/A | Waitlist module not built in current code: waitlist table has only id/timestamps; no model, screens or routes. Full programs block enrollment (capacity check) instead.
45 | Waitlist | WAIT-03 | Expired offer | 1. Let an offered waitlist entry pass its response window | Status updates to expired | Low | N/A | Waitlist module not built in current code: waitlist table has only id/timestamps; no model, screens or routes. Full programs block enrollment (capacity check) instead.
46 | Attendance | ATT-01 | Check in a child | 1. Staff checks in a child for today | check_in_time recorded; status=present | High | Pass | Checked in via Attendance Desk: check_in_time 08:40:00, status=present.
47 | Attendance | ATT-02 | Check out a child | 1. Staff checks out the same child later | check_out_time recorded | High | Pass | check_out_time 16:30:00 recorded; duration shown (7h 50m).
48 | Attendance | ATT-03 | Mark absent | 1. Mark a child absent for a day they didn't attend | status=absent saved for that date | Medium | Pass | status=absent saved for 2026-10-18.
49 | Attendance | ATT-04 | Daily attendance counts are accurate | 1. Compare the attendance report for a given day against manual check-ins | Present/absent/late counts match reality | Medium | Pass | Attendance Desk stats match today's records: recorded 1, in 0, checked out 1, late 0, absent 0, not checked in 2 of 3 enrolled.
50 | Child Daily Logs | LOG-01 | Log a nap | 1. Add a daily log with log_type=nap, start/end time, quality | Entry saves and displays correctly on the child's timeline | Medium | Pass | Retested after fix: nap saved with start/end (13:00–14:15, 1 hr 15 min) and Sleep Quality = Good; shown on the child's day timeline and Daily Logs list. Fixed: quality was previously discarded for naps; the log form now shows a Quality field labelled Appetite / Sleep Quality / Engagement by log type.
51 | Child Daily Logs | LOG-02 | Log a meal | 1. Add a daily log with log_type=meal, meal_type, items_served, amount_eaten | Meal-specific fields save; unrelated fields (quality) stay blank | Medium | Pass | meal_type, items_served, amount_eaten saved; quality left blank.
52 | Child Daily Logs | LOG-03 | Log activity participation | 1. Log an entry with log_type=activity linked to an activity_occurrence_id | Entry correctly references the occurrence; shows in that occurrence's participant list | Medium | Pass | Log references occurrence #26; child appears on that occurrence's page.
53 | Child Daily Logs | LOG-04 | Log an incident | 1. Add a daily log with log_type=incident and detailed notes | Notes saved in full; visible to authorized staff/admin | High | Pass | Incident notes (1112 chars) saved in full; visible to admin and staff.
54 | Child Daily Logs | LOG-05 | Daily timeline sorts correctly | 1. View a child's full day of logs | Entries display in chronological order by start_time | Low | Pass | Entries added out of order (17:10 then 07:50) display chronologically by start_time.
55 | Child Daily Logs | LOG-06 | Parent has read-only access to logs | 1. Login as parent 2. View own child's daily logs | Logs are visible but no edit controls are shown | Medium | Pass | Parent sees own child's logs (admin view 200 + parent app Today) read-only; POST blocked (403); other child's logs 403.
56 | Documents | DOC-01 | Upload a document | 1. Admin/staff uploads an immunization record for a child | File stored; document row created with correct doc_type | Medium | Pass | Uploaded via child edit form; file stored; document row doc_type=medical_form (no dedicated 'immunization' type — use Medical Form).
57 | Documents | DOC-02 | Expiry date displays | 1. Upload a document with an expiry_date | Expiry date shows correctly on the child's document list | Low | Pass | Retested after fix: expiry date (Jun 30, 2027) shows in the new Expiry column of the child's document list (Edit Child). Expired documents are flagged red, ones expiring within 30 days amber; no date shows "No expiry".
58 | Documents | DOC-03 | Parent cannot upload documents | 1. Login as parent 2. Attempt to upload a document | Action blocked/hidden | Medium | Pass | Parent upload blocked (update returned 403, edit form 403); no document created.
59 | Activities | ACT-01 | Create an activity | 1. Admin adds a new activity to the catalog (name, category, age range) | Activity saved and available for scheduling | Low | Pass | Activity saved (name, category, duration) and offered when scheduling an occurrence. Note: catalog has no age-range field.
60 | Activities | ACT-02 | Log an activity occurrence | 1. Schedule/log an occurrence for a program on a specific date | Occurrence saved with correct activity, program, date | Medium | Pass | Occurrence saved: activity, program and date 2026-10-23 correct.
61 | Activities | ACT-03 | Occurrence status update | 1. Mark an occurrence as completed / partial / cancelled | Status saves correctly | Low | Pass | Status saved for completed, partial and cancelled.
62 | Activities | ACT-04 | Monthly calendar view | 1. Open the admin's monthly activity view for a given month | All occurrences for that month display grouped by day, matching actual records | High | Pass | Monthly Activity Calendar loads for October 2026 with occurrences grouped by day (5 occurrence(s) in DB this month).
63 | Activities | ACT-05 | Attach media to an occurrence | 1. Upload a photo/video to an activity occurrence | Media saves and displays linked to that occurrence | Low | Pass | Photo saved (media_type=photo) and displayed on the occurrence page; also appears in parent app Photos for that program.
64 | Activities | ACT-06 | Child engagement reflected | 1. Log a child's engagement quality for an activity via the daily log | Correct engagement level shows against that child + occurrence | Low | Pass | Retested after fix: engagement entered on the activity log (Good) is saved and shows in the new Engagement column against the child on the activity occurrence page, and on the child's timeline / Daily Logs list.
65 | Drop-in Bookings | DROP-01 | Book drop-in for enrolled child | 1. Book a drop-in day for a child who already has an active enrollment | Booking created and linked to that child/parent | Medium | N/A | Drop-in Bookings module not built in current code (no table/model/screens). "Drop-In" exists only as an enrollment service type.
66 | Drop-in Bookings | DROP-02 | Book drop-in for a walk-in (no account) | 1. Create a drop-in booking with child_id and parent_id left blank, just contact notes | Booking saves successfully with both FKs null | High | N/A | Drop-in Bookings module not built in current code (no table/model/screens). "Drop-In" exists only as an enrollment service type.
67 | Drop-in Bookings | DROP-03 | Status progression | 1. Move a booking from booked → checked_in → completed | Each status transition saves correctly | Medium | N/A | Drop-in Bookings module not built in current code (no table/model/screens). "Drop-In" exists only as an enrollment service type.
68 | Drop-in Bookings | DROP-04 | Drop-in appears in manual invoice | 1. Create a manual invoice and select a completed drop-in booking | Line item is added with the correct daily_rate | Medium | N/A | Drop-in Bookings module not built in current code (no table/model/screens). "Drop-In" exists only as an enrollment service type.
69 | Billing - Daycare | BILL-01 | Create a daycare-only invoice | 1. Admin selects only active enrollment items for a child 2. Creates the invoice | Invoice type saves as "daycare"; total matches sum of selected items | High | Pass | Daycare-only invoice INV-20261021-0001: type=daycare, total ৳5,100 = sum of items. Note: items are entered/selected from the item catalog — invoices are not auto-built from active enrollments.
70 | Billing - Daycare | BILL-02 | Invoice type auto-classification | 1. Repeat BILL-01 exactly | type field correctly equals "daycare" (not therapy or mixed) | Medium | Pass | Type computed as "daycare" (derived from items, not stored).
71 | Billing - Daycare | BILL-03 | Record a full payment | 1. Record a payment equal to the invoice total | Invoice status updates to paid | High | Pass | Full cash payment recorded → status Paid, balance ৳0.
72 | Billing - Daycare | BILL-04 | Record a partial payment | 1. Record a payment less than the invoice total | Invoice remains outstanding for the correct remaining balance | High | Pass | Partial payment ৳1,200 of ৳3,000 → status Partially Paid, balance ৳1,800.
73 | Billing - Daycare | BILL-05 | State-funded line item is $0 | 1. Include a state-funded enrollment on an invoice | Line item shows unit_price/subtotal = 0.00 correctly | Medium | N/A | No state-funded enrollment concept in current code (no flag on enrollments/invoices). Manual line items also require amount ≥ 0.01.
74 | Billing - Daycare | BILL-06 | Invoice item math is correct | 1. Add multiple items with different quantities/prices to one invoice | subtotal and invoice total_amount both calculate correctly | High | Pass | Item amounts and invoice total_amount both ৳5,450.75. Note: UI has no quantity field (qty fixed at 1 per line).
75 | Therapy Wing Setup | THER-01 | Create a therapist staff record | 1. Admin creates a staff user with role=therapist and a specialization (SLT/ABA/OT) | Staff row saves with correct role, department=therapy, specialization | High | Pass | Retested after fix: Admin > Staff > Add Staff (role Therapist, dept Therapy, specialization SLT/OT) saves the staff row with correct role/department/specialization and a login account; the new therapist can sign in. Fixed: password was missing from validation (500 error). Password is now required (min 8, confirmed) on create; on edit, blank keeps the current password and a new one is now actually saved.
76 | Therapy Wing Setup | THER-02 | Therapy service catalog entry | 1. Admin adds a therapy service (e.g. "ABA Session") with duration and session_rate | Service saves and is selectable for booking | Medium | Pass | Service saved (45 min, ৳1,200) and selectable on the session booking form.
77 | Therapy Wing Setup | THER-03 | Existing staff unaffected by new columns | 1. Open a staff record created before this module existed | department defaults to "daycare"; specialization is null; nothing else changed | Medium | Pass | Existing staff (Tania Sultana) department=daycare, specialization=null.
78 | Therapy Wing Setup | THER-04 | Non-admin blocked from managing services | 1. Login as staff/parent 2. Attempt to edit the therapy services catalog | Access denied | Medium | Pass | Staff (create form/POST) and parent (index) all get 403.
79 | Therapy Sessions | TSES-01 | Book a therapy session | 1. Book a session for a child with a specific therapist and service, date/time | Session saves with status=scheduled | High | Pass | Session saved with status=scheduled (therapist specialization must match service type; overlaps are rejected).
80 | Therapy Sessions | TSES-02 | Mark session completed | 1. Update a scheduled session's status to completed, add notes | Status and notes save correctly | High | Pass | Status → completed; notes kept (status update form only changes status).
81 | Therapy Sessions | TSES-03 | Mark session cancelled/no-show | 1. Update a session's status to cancelled or no_show | Status saves correctly; session excluded from billing eligibility | Medium | Pass | cancelled and no_show saved; neither appears in billable sessions.
82 | Therapy Sessions | TSES-04 | Multiple same-day sessions allowed (by design) | 1. Book more than 8 sessions for one therapist on the same day | System allows it without blocking — confirms the deliberate "flexible, no hard cap" decision | Low | Pass | 9 non-overlapping sessions booked for one therapist on one day — no daily cap. (Overlapping times are still rejected.)
83 | Therapy Sessions | TSES-05 | booked_by is recorded | 1. Create a session as a specific logged-in user | booked_by correctly stores that user | Low | Pass | booked_by = logged-in user (admin@daycare.com).
84 | Therapy Packages | PKG-01 | Create a single-type package | 1. Admin creates a package (e.g. "OT — 4 Session Package") with a hand-set price | Package saves; total_sessions derived correctly as 4 from its items | High | Pass | Package saved with hand-set price ৳3,100; total_sessions derived = 4.
85 | Therapy Packages | PKG-02 | Create a custom combo package | 1. Admin creates a package with multiple item rows, e.g. 4 OT + 6 ABA + 8 SLT | All item rows save; derived total_sessions = 18 | High | Pass | 3 item rows saved (4 OT + 6 ABA + 8 SLT); total_sessions = 18.
86 | Therapy Packages | PKG-03 | Package total sessions is accurate | 1. Open any package with 2+ item rows | Displayed total equals the sum of session_count across its items — not a separately stored/edited number | Low | Pass | Total is derived from item session_count (no stored column); list shows 18.
87 | Therapy Packages | PKG-04 | Purchase a package for a child | 1. Select a child 2. Purchase an existing package template | A child_therapy_packages row is created with a snapshot of items (child_therapy_package_items) | High | Pass | child_therapy_packages row created with item snapshot (OT × 4).
88 | Therapy Packages | PKG-05 | Purchase price is editable | 1. During purchase, change the price away from the template's default price 2. Save | purchase_price stores the edited amount, not the template's original price | High | Pass | purchase_price stored as edited ৳2,800 (template price ৳3,100).
89 | Therapy Packages | PKG-06 | Remaining balance calculates correctly | 1. Complete 2 of 4 included OT sessions for a purchased package 2. Check remaining balance | Remaining shows 2 (included − completed), computed live, not a stored counter | High | Pass | Remaining = 2 (4 included − 2 completed), computed live. Retested with sessions booked from the package on the session form and marked completed.
90 | Therapy Packages | PKG-07 | Book a session against a package | 1. Book a new therapy session 2. Choose "from package" and select the child's active package | Session saves with child_therapy_package_id set to that package | High | Pass | Retested after fix: Therapy Sessions > New/Edit now has a Payment field — "Use package — oldest first", a specific package (shows "x of y left"), or "Pay per session". Session saves with child_therapy_package_id set to that package. Rejected with a message: another child's package, cancelled or expired package, package that doesn't cover the therapy, or no sessions left. Session page shows Payment = package.
91 | Therapy Packages | PKG-08 | Package-sourced session isn't billed again | 1. Complete a session booked from a package 2. Open the manual invoice / unbilled sessions screen | That session does NOT appear as a standalone billable item — it was already prepaid | High | Pass | Completed sessions booked from a package are excluded from the billable/unbilled list on Create Invoice (retested with sessions booked from the package in the UI).
92 | Therapy Packages | PKG-09 | Only completed sessions reduce balance | 1. Book a package session 2. Mark it cancelled or no_show instead of completed 3. Recheck remaining balance | Balance is unchanged — only completed sessions consume from the package | Medium | Pass | Balance unchanged (2) after a cancelled and a no_show session — only completed sessions count.
93 | Therapy Packages | PKG-10 | Oldest package consumed first (FIFO) | 1. Give a child two active packages with the same therapy type 2. Book a new session from a package | The older (earlier purchased_at) package's balance is drawn down first | Medium | Pass | Retested after fix: child with two active OT packages — "Use package — oldest first" drew sessions from the older package (earlier purchased_at) until its balance was used, then moved to the newer one. Scheduled sessions reserve a slot; cancelled / no-show give it back.
94 | Therapy Packages | PKG-11 | Leftover balance carries forward | 1. Purchase a second package for a child who still has unused sessions on an older one | Both packages remain active independently — no merge/migration; old balance is still usable | High | Pass | Second package purchased; both remain active independently and the old balance (2) is still there.
95 | Therapy Packages | PKG-12 | Existing balance shown before new purchase price is set | 1. Start a new package purchase for a child who already has remaining sessions | An info panel shows existing unused sessions before the admin finalizes the price | Medium | Pass | Retested after fix: Purchase Package form now shows an "Existing Balance" panel as soon as the child is picked (before the price is set): each active package with sessions left, purchase/expiry date, invoice no. and per-therapy "x of y left" (booked sessions noted). A child with none shows "OK to buy a new one".
96 | Therapy Packages | PKG-13 | Cancel a package | 1. Admin cancels an active child package | Status becomes cancelled; it no longer offers balance for new session bookings | Medium | Pass | Status → cancelled, and the cancelled package is no longer offered on the session form (booking it directly is rejected).
97 | Therapy Packages | PKG-14 | Non-admin blocked from package management | 1. Login as staff — attempt to create/edit a package or purchase one 2. Login as parent — view own child's package | Staff: view-only per therapy-packages permissions; Parent: read-only, own child only; neither can purchase/cancel | High | Pass | Agreed rule (product owner): staff may buy a package for a child and cancel it, but cannot create/edit package templates — Package Catalog create returns 403 for staff. Parent: read-only, own child only, cannot purchase/cancel (403). Retested: staff template create 403, staff purchase OK (with invoice), parent purchase 403.
98 | Therapy Billing | TBILL-01 | Unbilled sessions appear for selection | 1. Complete a therapy session 2. Open the manual invoice creation screen for that child | The completed session appears in the "unbilled" checklist | High | Pass | Completed standalone session appears in the "Include therapy sessions" list on Create Invoice.
99 | Therapy Billing | TBILL-02 | Billed session disappears from the unbilled list | 1. Invoice the session from TBILL-01 2. Reopen the invoice creation screen for the same child | That session no longer appears (whereDoesntHave invoiceItem check works) | High | Pass | Invoiced on INV-20261021-0005; no longer in the unbilled list.
100 | Therapy Billing | TBILL-03 | Therapy-only invoice | 1. Create an invoice selecting only therapy session items | Invoice type saves as "therapy" | Medium | Pass | Session-only invoice type = therapy.
101 | Therapy Billing | TBILL-04 | Mixed invoice | 1. Create an invoice selecting both enrollment and therapy session items together | Invoice type saves as "mixed"; both line item types appear on one invoice | High | Pass | Tuition + therapy session on one invoice; type = mixed. (Tuition is a manual/catalog item, not auto from enrollment.)
102 | Therapy Billing | TBILL-05 | Package purchase generates one invoice item | 1. Purchase a package for a child | Exactly one invoice_item is created immediately, with child_therapy_package_id set (prepaid) | High | Pass | Retested after fix: Child Packages > Purchase now creates one draft invoice (due in 7 days) for the child's primary parent with exactly one item for the purchase price, child_therapy_package_id set; the package is linked to that invoice. Buying a package on Create Invoice still gives one item. A ৳0 package or a child with no parent is saved without an invoice and the user is told.
103 | Therapy Billing | TBILL-06 | Package sessions excluded from per-session billing | 1. Complete several sessions drawn from an active package 2. Run the standalone therapy billing screen | None of those package-sourced sessions appear in the unbilled list — only true standalone sessions do | High | Pass | Same check as PKG-08: package-sourced completed sessions do not appear in the unbilled list; only standalone sessions do.
104 | Reports | REP-01 | Revenue report totals are accurate | 1. Run the Billing/Revenue report for a known date range | Total invoiced/collected/outstanding match a manual sum of those invoices | High | Pass | This month: invoiced ৳30,650.75, collected ৳4,200.00, outstanding ৳26,450.75 — match a manual sum.
105 | Reports | REP-02 | Revenue report type filter | 1. Filter the revenue report by type=therapy | Only therapy-relevant figures reflect per the intended filter logic | Medium | Pass | type=therapy lists only therapy invoices (2); totals reflect the filtered set.
106 | Reports | REP-03 | Outstanding invoices list is correct | 1. Run the Outstanding Invoices report | Only invoices with status sent/overdue appear, sorted most-overdue first | High | N/A | Outstanding Invoices report not built in current code (only Billing/Revenue and Activity Calendar reports exist). Outstanding balance can be filtered on Billing/Revenue by status.
107 | Reports | REP-04 | Days overdue calculation | 1. Check a specific overdue invoice's days_overdue value against today's date | Value matches an actual day-count calculation | Medium | N/A | No days_overdue calculation exists (depends on the Outstanding Invoices report — REP-03).
108 | Reports | REP-05 | Invoice auto-flip to overdue | 1. Let a sent invoice's due_date pass 2. Run the scheduled overdue-check job | Status updates from sent to overdue automatically | High | N/A | No scheduled overdue-check job exists (routes/console.php has no schedule); invoices are never auto-flipped to overdue. Status "sent" exists (set when a payment link is sent).
109 | Reports | REP-06 | Report totals row | 1. Check the summary/total row on each report | Totals correctly sum the visible rows | Medium | Pass | Print view totals row ৳32,250.75 equals the sum of listed (non-cancelled) rows. On-screen report shows totals in the summary cards (no table totals row).
110 | Announcements | ANN-01 | Audience targeting | 1. Staff posts an announcement with audience=parents | Only parent accounts see it; staff/admin-only announcements stay hidden from parents | Medium | Pass | Retested after fix: parents see only live parent/everyone notices on the parent app, home page and /admin/announcements; staff-only notices are hidden (also via audience filter, and by direct URL = 404). Create/edit/delete now require announcements.create (admins always): parents get 403 and see no buttons. Note: staff can post only if granted announcements.create in Role Permissions — tested: notice posted for parents then appears in the parent app.
111 | Announcements | ANN-02 | Expired announcement hides | 1. Set expires_at to a past date on an announcement | It no longer displays to any audience | Low | Pass | Expired notice hidden from parent app and public home page ticker (still listed for admins with status Expired).
112 | Announcements | ANN-03 | Permission-gated visibility | 1. Login as a role without announcements.view-any | Announcements page/menu item is inaccessible | Medium | Pass | User without announcements.view-any gets 403 (note: parent and staff roles both have this permission by default).
113 | Child Safety QR | SAFE-01 | Generate a safety tag | 1. From a child's profile, generate a new safety tag | A unique token and QR image are created and saved | High | Pass | Unique token (32 chars) and QR image created.
114 | Child Safety QR | SAFE-02 | Scan loads the public card | 1. Open the QR's URL in a browser with no login | The safety card page loads successfully, no auth required | High | Pass | Public card loads with no login.
115 | Child Safety QR | SAFE-03 | Card shows minimal info only | 1. Inspect the rendered public card | Only first name + phone numbers shown — no last name, no address, no medical notes | High | Pass | Child shown by first name only; no child last name, address, allergies or medical notes. Note: the emergency contact's full name is shown on the call button (e.g. "Zakir Rahman"), which can reveal the family surname.
116 | Child Safety QR | SAFE-04 | Call Guardian button works | 1. Tap/click the Call Guardian button on a mobile device | Correct parent phone number is dialed via tel: link | Medium | Pass | Call Guardian uses tel:01711000001 (primary guardian mobile).
117 | Child Safety QR | SAFE-05 | Found report with location | 1. Submit "I found this child" and allow location access | Report saves with latitude/longitude populated | High | Pass | Found report saved with lat/lng (23.7808000, 90.4170000).
118 | Child Safety QR | SAFE-06 | Found report without location | 1. Submit the same form but deny location permission | Report still saves successfully with lat/lng left null | Medium | Pass | Report saved with lat/lng null.
119 | Child Safety QR | SAFE-07 | Guardian receives the alert | 1. Submit a found report 2. Check the guardian's phone | SMS/WhatsApp alert arrives with a map link and finder's contact info | High | N/A | No SMS/WhatsApp provider integrated — found reports are saved (SAFE-05/06) but no alert is sent to the guardian, and there is no admin screen listing found reports yet.
120 | Child Safety QR | SAFE-08 | Deactivated tag returns 404 | 1. Deactivate a safety tag 2. Revisit its QR URL | Page returns 404, does not show stale child data | High | Pass | Deactivated tag URL returns 404.
121 | Security & Non-Functional | SEC-01 | Session regenerates on login | 1. Inspect the session ID before and after a successful login | Session ID changes after login (fixation protection) | Medium | Pass | AuthController calls session()->regenerate() after successful login (and on register); logout invalidates + regenerates token.
122 | Security & Non-Functional | SEC-02 | CSRF protection | 1. Attempt to submit a POST form without a valid CSRF token | Request is rejected (419 error) | High | Pass | POST without CSRF token rejected with 419. (Only SSLCommerz callback URLs are intentionally excluded.)
123 | Security & Non-Functional | SEC-03 | Public routes are rate-limited | 1. Rapidly hit a public /s/{token} URL more than 30 times in a minute | Requests beyond the limit are throttled/rejected | Medium | Pass | Request #31 within a minute returned 429 (limit 30/min).
124 | Security & Non-Functional | SEC-04 | Public page is not indexable | 1. View the safety card page's HTML source | A <meta name="robots" content="noindex, nofollow"> tag is present | Low | Pass | noindex, nofollow meta present on the safety card.
125 | Security & Non-Functional | SEC-05 | ID-guessing is blocked | 1. As a parent, try sequential child IDs in the URL that aren't theirs | Every unauthorized ID returns 403, not the child's data | High | Pass | All 5 other children's IDs return 403 for the parent; parent app child switch also rejects others.
126 | Security & Non-Functional | SEC-06 | Demo routes removed before production | 1. Check the production route list for any /demo/* AdminLTE routes | None are present | Low | Pass | Retested after fix: AdminLTE demo pages and the public /docs viewer are no longer registered (/demo/* and /docs return 404). Controlled by ADMINLTE_DEMO / ADMINLTE_DOCS in .env (default off).